Primevolta Hardware Solutions
Detailed Billing Schedule Agreement
Client: FinSecure Services
Date: 11th December 2025

1. Purpose

This Billing Schedule Agreement (“Agreement”) is entered into between Primevolta Hardware Solutions (“Vendor”) and FinSecure Services (“Client”) to define detailed procedures for billing, invoicing, and payments. The purpose of this Agreement is to:

- Ensure proper obligation tracking for all delivered hardware.

- Prevent revenue leakage by clearly aligning invoices with delivered goods, milestones, and service obligations.

- Provide a structured billing and dispute resolution mechanism to maintain transparency and accountability.

2. Scope of Agreement

This Agreement covers the supply of:

- Hardware components including servers, storage arrays, networking devices, and electronic peripherals.

- Multi-site deliveries for BFSI branch rollouts.

- Associated services including installation, testing, and warranty support.

The Agreement applies to all purchase orders (POs) issued by the Client and accepted by the Vendor, including one-time, recurring, and bulk supply orders.

3. Billing Schedule & Frequency

3.1 Standard Billing:

- Monthly Invoicing: For ongoing supply contracts, invoices will be raised on the last business day of each month.

- Delivery-Based Billing: For one-time supply orders exceeding INR 5,00,000, invoices will be issued upon confirmed delivery to the Client’s site(s).

3.2 Staged / Milestone Billing:
For projects involving multiple sites or large-scale deployments exceeding INR 50,00,000:

| Milestone | Billing % | Conditions | Documentation Required |
| --- | --- | --- | --- |
| PO Acceptance | 20% | Upon issuance of confirmed Purchase Order | PO copy, Vendor confirmation |
| Hardware Dispatch | 30% | Upon shipment to the Client site | Delivery challans, logistics details |
| On-Site Installation | 30% | Upon completion of installation at each site | Installation report, site acceptance certificate |
| User Acceptance Testing (UAT) | 20% | Upon successful UAT and sign-off by Client | UAT report, Client sign-off |

3.3 Payment Terms:

- Standard credit period: 30 calendar days from invoice date.

- Late payment penalty: 1.5% per month on overdue amounts.

- Advance payments will not exceed 20% of total PO unless mutually agreed in writing.

4. Invoice Details & Credit Notes

4.1 Invoice Components:
All invoices must contain the following:

- Vendor and Client details

- Invoice number and date

- PO number and reference

- Itemized list of delivered goods/services

- Unit price, total amount, applicable taxes, and levies

- Delivery dates and sites

- Reference to applicable milestone, if any

4.2 Credit Notes:

- Credit notes will be issued for returns, short shipments, or billing errors.

- The credit note will reference the original invoice and clearly state the reason for adjustment.

- Credit notes are valid for 90 days from the date of issuance unless otherwise agreed.

5. Obligations of Vendor

- Deliver goods as per the specifications and timelines mentioned in the PO.

- Maintain accurate records of shipped, installed, and tested hardware.

- Provide complete supporting documentation including delivery notes, installation certificates, and warranty cards.

- Notify the Client of any deviations in delivery schedule at least 7 business days in advance.

6. Obligations of Client

- Process invoices within the agreed payment timeline.

- Notify the Vendor of any discrepancies in invoices or deliveries within 7 business days.

- Approve milestone payments and site acceptance certificates promptly to avoid revenue delays.

- Provide access to sites for installation and testing activities.

7. Dispute Resolution

- All invoice or billing disputes must be documented and sent to the Vendor in writing.

- Both parties will attempt resolution within 15 business days from receipt of dispute notice.

- If unresolved, disputes will escalate to senior management of both parties, whose decision shall be final.

8. Reporting & Revenue Tracking

- Vendor shall provide monthly revenue tracking reports detailing billed, unbilled, and pending payments.

- Client may request quarterly reconciliation reports to ensure alignment between delivered hardware, invoices, and payments.

- Both parties shall maintain a shared ledger or digital record of milestone completion, invoices, and payments for audit purposes.

9. Confidentiality

- Billing information, payment records, and financial details shall remain confidential.

- Disclosure is only allowed with written consent or if required by law.

10. Amendment and Termination

- Any amendment must be mutually agreed in writing.

- Either party may terminate the agreement with 30 days’ notice, without affecting outstanding invoices or milestones.

- Termination does not absolve any pending financial obligations.

11. Governing Law

- This Agreement shall be governed by the laws of India.

- Disputes will be under the jurisdiction of courts located in [City, State].

Signatures:

| Party | Name | Designation | Signature | Date |
| --- | --- | --- | --- | --- |
| Primevolta Hardware Solutions |  |  |  |  |
| FinSecure Services |  |  |  |  |